## Backlog
Epic ID | Epic Name | Story ID | User Story | Acceptance Criteria | Priority | Points | Release | Status | Assignee | Sprint | Start Date | Due Date | Notes
0 | Discovery & Architecture Spikes | SPIKE-1 | As an engineering team, I want to decide between NestJS and FastAPI for the backend API, so that we commit to one technology stack before development starts. | - Comparison against team skills, ecosystem, and performance needs is documented - Decision is approved by the tech lead and recorded in the architecture doc | Must | 2 | Release 1 | Not Started
0 | Discovery & Architecture Spikes | SPIKE-2 | As an engineering team, I want to choose between Apache AGE and Neo4j for the graph database, so that the ingestion and retrieval layers can be built on a confirmed technology. | - Trade-off analysis (cost, hosting, query language, team familiarity) is documented - Decision is recorded and shared with the team | Must | 3 | Release 1 | Not Started
0 | Discovery & Architecture Spikes | SPIKE-3 | As an engineering team, I want to select a vector store (pgvector, Qdrant, or Weaviate), so that embeddings can be stored and queried efficiently. | - Comparison of shortlisted options is documented - Decision aligns with the chosen graph DB and hosting strategy | Must | 3 | Release 1 | Not Started
0 | Discovery & Architecture Spikes | SPIKE-4 | As an engineering team, I want to define the multi-tenant isolation strategy (row-level vs schema-level), so that tenant data isolation is designed correctly from day one. | - Isolation approach is documented for both the graph DB and vector store - Approach is validated against the 'no cross-tenant access' requirement | Must | 3 | Release 1 | Not Started
0 | Discovery & Architecture Spikes | SPIKE-5 | As a product owner, I want to confirm which LLM providers will be supported at launch, so that the LLM abstraction layer and BYOK feature can be scoped correctly. | - List of supported providers (e.g., Anthropic, OpenAI) is approved - Decision documented in the architecture doc | Must | 2 | Release 1 | Not Started
0 | Discovery & Architecture Spikes | SPIKE-6 | As a product owner, I want to define the billing model and quota structure, so that usage limits and monetization can be implemented consistently. | - Pricing tiers and quota rules are documented - Model is validated with stakeholders | Should | 3 | Release 1 | Not Started
0 | Discovery & Architecture Spikes | SPIKE-7 | As a product owner, I want to confirm the final SLA target for platform uptime, so that infrastructure and on-call plans can be sized accordingly. | - SLA percentage is agreed upon (e.g., 99.5%) - SLA is documented and communicated to the team | Should | 2 | Release 1 | Not Started
0 | Discovery & Architecture Spikes | SPIKE-8 | As a product owner, I want to define the data retention policy for documents and conversation history, so that the platform stays compliant and predictable in storage cost. | - Retention periods for documents and chat history are documented - Deletion/archival mechanism is scoped | Should | 2 | Release 1 | Not Started
0 | Discovery & Architecture Spikes | SPIKE-9 | As an engineering team, I want to define the monitoring and alerting strategy, so that the observability epic can be implemented against a clear plan. | - Tooling (e.g., Prometheus/Grafana or a hosted alternative) is selected - Key metrics and alert thresholds are drafted | Should | 3 | Release 1 | Not Started
1 | Tenant Onboarding & Authentication | US-1.1 | As a prospective tenant, I want to sign up for an account, so that I can start using the platform. | - Sign-up validates email format and password strength - A new tenant record and isolated workspace are created on success - A confirmation email is sent | Must | 5 | Release 1 | Not Started
1 | Tenant Onboarding & Authentication | US-1.2 | As a tenant admin, I want to log in securely to my account, so that I can access my dashboard. | - Login uses JWT/OAuth2-based authentication - Invalid credentials show a generic error message - Sessions expire after a defined inactivity period | Must | 3 | Release 1 | Not Started
1 | Tenant Onboarding & Authentication | US-1.3 | As a tenant admin, I want to go through a guided onboarding flow (self-service or by invitation), so that I can set up my chatbot with minimal friction. | - Wizard covers account setup, first data source, and chatbot basics - Invitation-based onboarding pre-fills the relevant tenant context | Should | 5 | Release 1 | Not Started
1 | Tenant Onboarding & Authentication | US-1.4 | As a tenant admin, I want to invite team members to my organization, so that we can collaborate on managing the chatbot. | - Invite is sent by email with a secure sign-up link - Invited user is assigned a default role (e.g., Viewer) | Should | 5 | Release 1 | Not Started
2 | Data Source Management & Ingestion Pipeline | US-2.1 | As a tenant admin, I want to upload documents (PDF, DOCX, TXT, CSV), so that the chatbot can be trained on my company data. | - Upload accepts supported file types and rejects others clearly - Files are stored in tenant-isolated object storage - Upload automatically triggers the ingestion pipeline | Must | 8 | Release 1 | Not Started
2 | Data Source Management & Ingestion Pipeline | US-2.2 | As a tenant admin, I want to add a URL to be crawled, so that my website content becomes part of the chatbot's knowledge. | - Provided URL is validated and queued for crawling - Crawled pages are chunked through the same pipeline as documents | Should | 8 | Release 1 | Not Started
2 | Data Source Management & Ingestion Pipeline | US-2.3 | As a tenant admin, I want to manually enter text as a knowledge source, so that I can quickly add small pieces of information without a file. | - A text entry form saves content directly into the ingestion pipeline - Entered text appears in the source list like any other source | Could | 3 | Release 1 | Not Started
2 | Data Source Management & Ingestion Pipeline | US-2.4 | As an ingestion pipeline, I want to parse, chunk, and extract entities and relations from ingested content, so that a knowledge graph can be built automatically. | - Parsing supports all accepted file types and crawled pages - Entity/relation extraction uses a configurable LLM step - Failures are logged and retried without blocking the queue | Must | 13 | Release 1 | Not Started
2 | Data Source Management & Ingestion Pipeline | US-2.5 | As an ingestion pipeline, I want to generate embeddings and index them into an isolated vector store per tenant, so that retrieval stays fast and strictly tenant-scoped. | - Embeddings are written only to the requesting tenant's namespace/schema - Indexing status is reported back to the source record | Must | 13 | Release 1 | Not Started
2 | Data Source Management & Ingestion Pipeline | US-2.6 | As a tenant admin, I want to view the list of imported sources and their indexing status, so that I can track ingestion progress. | - List shows source name, type, upload date, and status - Status updates in near real-time | Must | 5 | Release 1 | Not Started
2 | Data Source Management & Ingestion Pipeline | US-2.7 | As a tenant admin, I want to delete a source, so that outdated or incorrect data is removed from the knowledge base. | - Deleting a source removes its chunks, embeddings, and graph nodes - Action requires confirmation | Must | 5 | Release 1 | Not Started
2 | Data Source Management & Ingestion Pipeline | US-2.8 | As a tenant admin, I want to re-trigger indexing for a source, so that I can refresh the knowledge base after the source content changes. | - Re-index replaces previous embeddings/graph data for that source - Re-index respects the same isolation guarantees as initial ingestion | Should | 3 | Release 1 | Not Started
3 | Chatbot Configuration & Personalization | US-3.1 | As a tenant admin, I want to set the chatbot's name, avatar, and welcome message, so that it matches my brand identity. | - Changes are reflected immediately in the widget preview - Avatar upload supports common image formats with a size limit | Should | 3 | Release 2 | Not Started
3 | Chatbot Configuration & Personalization | US-3.2 | As a tenant admin, I want to define the chatbot's tone/persona and supported languages, so that it communicates the way I want with my users. | - Persona setting influences the system prompt sent to the LLM - Multiple languages can be selected and one set as default | Should | 5 | Release 2 | Not Started
3 | Chatbot Configuration & Personalization | US-3.3 | As a tenant admin, I want to configure retrieval parameters (Top-K, graph/vector weighting, max response length), so that I can tune answer quality and cost. | - Changes apply to subsequent queries without redeployment - Sensible defaults are pre-filled for non-technical users | Could | 8 | Release 2 | Not Started
3 | Chatbot Configuration & Personalization | US-3.4 | As a tenant admin, I want to bring my own LLM API key (BYOK) or use platform-provided credits, so that I control cost and choice of provider. | - BYOK keys are stored encrypted and never re-displayed after entry - The platform clearly blocks or falls back when credits are exhausted | Must | 8 | Release 2 | Not Started
4 | Public API & Developer Access | US-4.1 | As a developer, I want to send a chat message via REST API and receive a GraphRAG-based response, so that I can integrate the chatbot into my own application. | - Endpoint accepts a message and a tenant-scoped API key - Response is returned within the 3-5 second performance target | Must | 13 | Release 1 | Not Started
4 | Public API & Developer Access | US-4.2 | As a developer, I want to manage conversation sessions and history via API, so that I can build multi-turn conversational experiences. | - Sessions are created, retrieved, and closed via dedicated endpoints - History is scoped to the tenant and the end user | Must | 8 | Release 1 | Not Started
4 | Public API & Developer Access | US-4.3 | As a developer, I want to manage data sources programmatically via API, so that ingestion can be automated from my own systems. | - API supports create, list, delete, and re-index operations on sources - Same validation rules apply as in the dashboard | Should | 8 | Release 1 | Not Started
4 | Public API & Developer Access | US-4.4 | As a tenant admin, I want to generate, rotate, and revoke API keys, so that I can control programmatic access securely. | - Newly generated keys are shown once and stored hashed - Revoked keys are rejected immediately by the API gateway | Must | 5 | Release 1 | Not Started
4 | Public API & Developer Access | US-4.5 | As a platform, I want to enforce rate limiting and per-key usage quotas, so that abuse and runaway costs are prevented. | - Requests beyond the limit receive a standard 429 response - Quota usage is visible to the tenant admin | Must | 8 | Release 1 | Not Started
4 | Public API & Developer Access | US-4.6 | As a developer, I want access to OpenAPI/Swagger documentation, so that I can integrate quickly and correctly. | - Documentation is auto-generated from the API definitions - Docs include authentication and example requests/responses | Should | 5 | Release 1 | Not Started
4 | Public API & Developer Access | US-4.7 | As a developer, I want an optional GraphQL endpoint alongside REST, so that I can query the chatbot and data in a more flexible way. | - GraphQL schema mirrors core REST capabilities (chat, sessions, sources) - Same auth and rate-limiting rules apply as REST | Could | 8 | Release 1 | Not Started
5 | Embeddable Micro-Frontend Widget | US-5.1 | As a tenant admin, I want to copy a script or Web Component snippet, so that I can embed the chatbot on my website with minimal effort. | - Snippet includes the tenant ID and a public widget key - Widget loads asynchronously without blocking the host page | Must | 8 | Release 2 | Not Started
5 | Embeddable Micro-Frontend Widget | US-5.2 | As a tenant admin, I want to configure the widget's theme, colors, position, and language through the snippet, so that it fits my site's design and audience. | - Configuration options are documented with examples - Invalid configuration values fall back to sensible defaults | Should | 5 | Release 2 | Not Started
5 | Embeddable Micro-Frontend Widget | US-5.3 | As an end user, I want the widget to render responsively on desktop and mobile without breaking the host site's styles, so that I have a smooth chat experience anywhere. | - Widget styles are isolated using Shadow DOM - Layout adapts correctly at common breakpoints | Must | 8 | Release 2 | Not Started
5 | Embeddable Micro-Frontend Widget | US-5.4 | As an end user, I want the widget to function without iframe-related issues, so that interactions such as scrolling, focus, and resizing feel native. | - No iframe is used for the core widget experience - Keyboard and screen-reader navigation work as expected | Must | 5 | Release 2 | Not Started
6 | Tenant Dashboard & Analytics | US-6.1 | As a tenant admin, I want to see analytics on messages sent, active users, and tokens consumed, so that I can monitor chatbot usage and value. | - Dashboard shows daily/weekly/monthly trends - Data refreshes at least once per day | Should | 8 | Release 2 | Not Started
6 | Tenant Dashboard & Analytics | US-6.2 | As a tenant admin, I want to manage users within my organization with Admin, Editor, and Viewer roles, so that I can control who can change versus just view settings. | - Role permissions are enforced on every relevant action - Removing a user immediately revokes their dashboard access | Must | 8 | Release 2 | Not Started
6 | Tenant Dashboard & Analytics | US-6.3 | As a tenant admin, I want to view my current consumption, quotas, and billing status, so that I can manage costs proactively. | - Consumption view matches usage tracked by the API/quota system - A near-quota state is visually flagged | Should | 5 | Release 2 | Not Started
7 | Billing & Quotas | US-7.1 | As a tenant admin, I want to view my billing plan and past invoices, so that I understand what I am being charged for. | - Invoice history is listed with downloadable receipts - Current plan and renewal date are clearly shown | Could | 5 | Release 3 | Not Started
7 | Billing & Quotas | US-7.2 | As a platform, I want to enforce usage quotas per tenant based on their plan, so that resource usage stays within contracted limits. | - Quota checks run before expensive operations (ingestion, chat calls) - Tenant is notified when approaching or exceeding quota | Should | 8 | Release 3 | Not Started
8 | Super Admin / Platform Administration | US-8.1 | As a super admin, I want to create, suspend, and delete tenants, so that I can manage the full tenant lifecycle. | - Suspending a tenant blocks API and widget access without deleting data - Deleting a tenant removes all associated data across every store | Must | 8 | Release 3 | Not Started
8 | Super Admin / Platform Administration | US-8.2 | As a super admin, I want to monitor global system health, ingestion queues, and per-tenant resource usage, so that I can ensure platform stability. | - A single view surfaces queue backlogs and failing jobs - Per-tenant resource usage is visible for capacity planning | Should | 8 | Release 3 | Not Started
8 | Super Admin / Platform Administration | US-8.3 | As a super admin, I want a global view of usage and billing across all tenants, so that I can track platform-wide business metrics. | - View aggregates usage and revenue figures across tenants - Data can be filtered by time period and plan tier | Should | 5 | Release 3 | Not Started
9 | Multi-Tenant Isolation & Security | US-9.1 | As a platform, I want every API request and retrieval query to be scoped by tenant_id, so that no cross-tenant data leakage can occur. | - tenant_id is enforced at the API gateway and the data-access layer - Automated tests verify one tenant cannot retrieve another tenant's data | Must | 13 | Release 1 | Not Started
9 | Multi-Tenant Isolation & Security | US-9.2 | As a platform, I want data encrypted at rest and in transit, so that tenant data is protected against unauthorized access. | - All storage layers use encryption at rest - All external traffic uses TLS | Must | 8 | Release 1 | Not Started
9 | Multi-Tenant Isolation & Security | US-9.3 | As a platform, I want JWT/OAuth2-based authentication with input validation and sanitization, so that the system is protected against common attack vectors. | - All endpoints reject unauthenticated requests unless explicitly public - Inputs are validated and sanitized before reaching the database or LLM layer | Must | 8 | Release 1 | Not Started
10 | Scalability, Performance & Observability | US-10.1 | As a platform, I want ingestion workers and query services to scale horizontally, so that the platform can support many tenants without a dedicated architecture per client. | - Workers and API services run as independently scalable containers - Load testing confirms horizontal scaling improves throughput | Should | 13 | Release 3 | Not Started
10 | Scalability, Performance & Observability | US-10.2 | As a platform, I want large file processing to run asynchronously, so that uploads never block the user interface. | - Upload returns immediately with a 'processing' status - The user can navigate away and later see the completed status | Must | 8 | Release 3 | Not Started
10 | Scalability, Performance & Observability | US-10.3 | As an end user, I want chatbot responses within 3-5 seconds including retrieval and generation, so that the experience feels responsive. | - Performance is measured under representative load - A performance budget is documented per pipeline stage | Must | 8 | Release 3 | Not Started
10 | Scalability, Performance & Observability | US-10.4 | As a platform team, I want logs, metrics, and tracing available per tenant and per service, so that issues can be diagnosed quickly. | - Each request is traceable end-to-end with a correlation ID - Dashboards exist for the key services (API, ingestion, LLM layer) | Should | 8 | Release 3 | Not Started
11 | Infrastructure & Deployment | US-11.1 | As a DevOps engineer, I want Docker and Kubernetes-ready deployment configurations, so that the platform can be deployed consistently across environments. | - Each service has a Dockerfile and a Compose entry for local development - Kubernetes manifests or Helm charts exist for staging/production | Must | 8 | Release 1 | Not Started
11 | Infrastructure & Deployment | US-11.2 | As a DevOps engineer, I want a CI/CD pipeline, so that releases are automated, tested, and reliable. | - Pipeline runs tests and builds on every merge to main - Deployment to staging is automated; production is gated by approval | Must | 8 | Release 1 | Not Started
12 | Documentation | US-12.1 | As a developer, I want architecture and integration documentation (API guide, widget integration guide, architecture overview), so that I can understand, integrate with, and extend the system. | - Documentation covers API auth, endpoints, and the widget snippet - The architecture overview stays up to date with major changes | Should | 5 | Release 3 | Not Started

## Dashboard
GraphRAG Chatbot Platform — Progress Dashboard
Live totals below are calculated from the Backlog sheet — just keep Status up to date.
Overall Progress
Total Story Points | 346
Completed Story Points | 0
% Complete (Points) | 0%
Total Stories | 54
Completed Stories | 0
In Progress | 0
Blocked | 0
Not Started | 54
Progress by Epic
Epic | Total Pts | Done Pts | % Complete | Stories | Done Stories
0. Discovery & Architecture Spikes | 23 | 0 | 0% | 9 | 0
1. Tenant Onboarding & Authentication | 18 | 0 | 0% | 4 | 0
2. Data Source Management & Ingestion Pipeline | 58 | 0 | 0% | 8 | 0
3. Chatbot Configuration & Personalization | 24 | 0 | 0% | 4 | 0
4. Public API & Developer Access | 55 | 0 | 0% | 7 | 0
5. Embeddable Micro-Frontend Widget | 26 | 0 | 0% | 4 | 0
6. Tenant Dashboard & Analytics | 21 | 0 | 0% | 3 | 0
7. Billing & Quotas | 13 | 0 | 0% | 2 | 0
8. Super Admin / Platform Administration | 21 | 0 | 0% | 3 | 0
9. Multi-Tenant Isolation & Security | 29 | 0 | 0% | 3 | 0
10. Scalability, Performance & Observability | 37 | 0 | 0% | 4 | 0
11. Infrastructure & Deployment | 16 | 0 | 0% | 2 | 0
12. Documentation | 5 | 0 | 0% | 1 | 0
Progress by Priority
Priority | Total Pts | Done Pts | % Complete
Must | 205 | 0 | 0%
Should | 117 | 0 | 0%
Could | 24 | 0 | 0%
Story Status Breakdown
Status | Stories | Points
Not Started | 54 | 346
In Progress | 0 | 0
In Review | 0 | 0
Blocked | 0 | 0
Done | 0 | 0

## How to use
How to use this tracker
1. Backlog sheet
This is the full product backlog (54 items across 13 epics), carried over from the product backlog document.
Blue-gray headers (columns A-H) are the backlog definition — epic, story, acceptance criteria, priority, points, planned release. Leave these as-is.
Orange headers (columns I-N) are for your team to fill in and update as work progresses: Status, Assignee, Sprint, Start Date, Due Date, Notes.
Status is a dropdown: Not Started, In Progress, In Review, Blocked, Done. The cell colors automatically once you pick a value.
Sprint is a dropdown (Backlog, Sprint 0-11) matching the release plan's suggested sprint ranges.
Use the filter arrows on row 1 to view one epic, one assignee, or one status at a time.
2. Dashboard sheet
Everything here is a live formula pulling from the Backlog sheet — it updates automatically as you change Status.
Overall Progress: total points, completed points, and story counts by status.
Progress by Epic / by Priority: where the team's effort stands, broken down two ways.
Charts: points completed vs. total per epic, and a status breakdown pie chart.
3. Suggested workflow
At sprint planning, set the Sprint column for the stories you are committing to.
As work starts, set Assignee and move Status to 'In Progress', then 'In Review', then 'Done'.
Check the Dashboard sheet in stand-ups or before a manager update — no manual counting needed.